## Project Plan and Gantt
Project Name | Powershell
Project Manager | Đinh Tấn Vương
Project Deliverable | 17/10/2016
Scope Statement:
Start Date | 2016-09-14
End Date | 2015-10-17
Overall Progress | 30%
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | Đinh Tấn Vương | 2016-09-14 | 2016-09-15 | 1 | Complete
Agree on objectives | Đinh Tấn Vương | 2016-09-15 | 2016-09-16 | 1 | Complete
Detailed Reqs. | Đinh Tấn Vương | 2016-09-17 | 2016-09-18 | 1 | Complete
Understanding CIM and WMI | Đinh Tấn Vương | 2016-09-19 | 2016-09-20 | 1 | Complete
Working with XML | Đinh Tấn Vương | 2016-09-21 | 2016-09-22 | 1 | Complete
Working with COM | Đinh Tấn Vương | 2016-09-23 | 2016-09-24 | 1 | Complete
Working with .NET objects | Đinh Tấn Vương | 2016-09-24 | 2016-09-26 | 2 | Complete
Creating Windows PowerShell Modules | Đinh Tấn Vương | 2016-09-26 | 2016-09-29 | 3 | in-process
Script debugging and error handling | Đinh Tấn Vươngg | 2016-09-30 | 2016-10-03 | 3 | Not started
Code(Lấy IP Remote PC trong mạng LAN) | Đinh Tấn Vương | 2016-10-04 | 2016-10-14 | 10 | Not started
Testing | Đinh Tấn Vương | 2016-10-14 | 2016-10-17 | 3 | Not started
Launch |  | 2016-10-17 | 2016-10-17 | 0

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address
Đinh Tấn Vương | Team Leader, Developer | 1. Lấy IP hiện có trong mạng để remote PC (code) 2. Write document | dinhtanvuong991996hcm@gmail.com

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team